## Smile Architects Test Cases
Target Completion | Test ID | Module | Testing Step | Path | Description | Tester | Status | Expected Result | Actual Result | Failure Scenario | Test Data (i.e. inputs) | Testers Comments | Date Tested | Test Result (Cycle 1) | Test Result (Cycle 2) | Test Result (Cycle 3) | Defect Status | Date found | Date Due | Defect Severity | Fixed by
Smile Architects Application
2022-04-12 | TS1 | Application Login | 1 | Success | Login to the new Smile Architects application using the user name and password. - User Tool | Daniel Torres | Success | Success | Success |  | Username/ Password | Application Login works with username and password | 2022-03-24 | Success | Success | Success | None | None | 2022-04-12 | None | N/A
2022-04-12 | TS2 | Booking Appointment | 2 | Success | Add a new appointment to the system | Daniel Torres | Success | Success | Success |  | Time/Date | Allows customer to book an apointment with the application using time/date data | 2022-03-24 | Success | Success | Success | None | None | 2022-04-12 | None | N/A
2022-04-12 | TS3 | Publish schedule of available appointments that can be booked | 3 | Success | An employee wants to publish a schedule of available appointments | Daniel Torres | Failed | Success | Failed | Schedule does not show up in frontend | Time/Date | Schedule does not show up on patient side | 2022-03-24 | Failed | Success | Success | Defective | 2022-03-24 | 2022-04-12 | Low | 2022-03-26
2022-04-12 | TS4 | View Patient Information for Appointments | 4 | Success | An employee wants to view patient information for upcoming appointment | Daniel Torres | Success | Success | Success |  | First Name / Last Name / Email | Business wants to view patient information for upcoming appointments | 2022-03-24 | Success | Success | Success | None | None | 2022-04-12 | None | N/A
2022-04-12 | TS5 | View schedule for the week | 5 | Success | An employee wants to view schedule for upcoming appointments | Daniel Torres | Success | Success | Success |  | Time/Date and Patient Information | Through the application the business can view schedule for the week and upcoming weeks | 2022-03-24 | Success | Success | Success | None | None | 2022-04-12 | None | N/A
2022-04-12 | TS6 | Unpublish Schedule | 6 | Success | An employee wants to unpublish a schedule of appointment times | Daniel Torres | Failed | Success | Failed | Schedule stays published | Time/Date and Patient Information | Schedule does not unpublish when clicking the button | 2022-03-26 | Failed | Success | Success | Defective | 2022-03-26 | 2022-04-12 | Low | 2022-03-27
2022-03-26 | Smile Architects Application
2022-04-12 | TS7 | Copy a week | 7 | Success | An employee wants to copy a schedule of a week | Daniel Torres | Success | Success | Success |  | Time/Date and Patient Information | The Business wants to Copy an existing schedule of a week to another week | 2022-03-26 | Success | Success | Success | None | None | 2022-04-12 | None | N/A
2022-04-12 | TS8 | Delete a day | 8 | Success | An employee wants to delete a schedule of a day | Daniel Torres | Success | Success | Success |  | Time/Date and Patient Information | The Business wants Appointments of a day is now deleted from the system when they are booked | 2022-03-26 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS9 | Copy a day | 9 | Success | An employee wants to copy a schedule of a day | Daniel Torres | Success | Success | Success |  | Time/Date and Patient Information | The Business wants the schedule of a day is now copied to another day of the week | 2022-03-26 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS10 | Delete Appointment Time Slot | 10 | Success | Employee wants to remove a timeslot | Daniel Torres | Success | Success | Success |  | Time/Date and Patient Information | The Business wants to remove a timeslot from the system | 2022-03-26 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS11 | Delete Employee | 11 | Success | Remove the employee record from the system | Daniel Torres | Failed | Success | Failed | Unable to delete employee | Employee Credentials such as username/password | Clicking delete button does not delete employee | 2022-03-26 | Failed | Success | Success | Defective | 2022-03-26 | 2022-04-08 | Low | 2022-03-27
2022-04-12 | TS12 | Modify Employee | 12 | Success | Edit the employee’s record in the system | Daniel Torres | Success | Success | Success |  | Employee Credentials such as username/password | The Business wants to edit employee information in the system | 2022-03-26 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS13 | Add Employee | 13 | Success | A new employee will be added to new system | Daniel Torres | Success | Success | Success |  | Employee Credentials such as username/password | The business wants to add a new employee within their application | 2022-03-26 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS14 | Cancel Appointment | 14 | Success | An employee will cancel an appointment | Daniel Torres | Success | Success | Success |  | Employee Credentials such as username/password also time/date | The business wants to cancel an appointment for a customer | 2022-03-31 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS15 | Create Appointment Time Slot | 15 | Success | Add a new appointment to the system | Daniel Torres | Success | Success | Success |  | Time/Date and Patient Information | The business wants appointments added to the system once customer books them | 2022-04-01 | Success | Success | Success | None | None | 2022-04-08 | None | N/A
2022-04-12 | TS16 | Reset Password | 16 | Success | Employee wants to reset their password | Daniel Torres | Success | Success | Success |  | Employee Crenditals such as username/password | Password reset succesfully & tested login with new password | 2022-04-10 | Success | Success | Success
2022-04-12 | TS17 | End of Test | 17 | Success | End of Test
Send a Canned Message Update to the Public Sector Team
Send an Attachment to the Public Sector Team

## Task Regression Test Cases
Sl. No. | Test Case ID | Module | Test Case Name | Test Data | Pre-requisites | Test Step | Expected Result
1 | TS1 | 1 | Application Login | Username/ Password |  | 1 | Application Login works with username and password
2 | TS2 | 2 | Booking Appointment | Time/Date | Appointments needs to be visible for booking | 2 | Allows customer to book an apointment with the application using time/date data
3 | TS3 | 3 | Publish schedule of available appointments that can be booked | Time/Date | Appointments needs to be visible for booking | 3 | The Business wants to publish a schedule of available appointments so they can see their customers
4 | TS4 | 4 | View Patient Information for Appointments | First Name / Last Name / Email | Patient must have booked an appointment already | 4 | Business wants to view patient information for upcoming appointments
5 | TS5 | 5 | View schedule for the week | Time/Date and Patient Information | Appointment must be in system already | 5 | Through the application the business can view schedule for the week and upcoming weeks
6 | TS6 | 6 | Unpublish Schedule | Time/Date and Patient Information | Appointments needs to be visible for booking | 6 | The Business wants the schedule unpublished and hidden from patients
7 | TS7 | 7 | Copy a week | Time/Date and Patient Information | Appointments needs to be added to a week | 7 | The Business wants to Copy an existing schedule of a week to another week
8 | TS8 | 8 | Delete a day | Time/Date and Patient Information | Day of appointments needs to be in the system | 8 | The Business wants Appointments of a day is now deleted from the system when they are booked
9 | TS9 | 9 | Copy a day | Time/Date and Patient Information | Day of appointments needs to be in the system | 9 | The Business wants the schedule of a day is now copied to another day of the week
10 | TS10 | 10 | Delete Appointment Time Slot | Time/Date and Patient Information | Appointment must be in the current system and not booked yet | 10 | The Business wants to remove a timeslot from the system
11 | TS11 | 11 | Delete Employee | Employee Credentials such as username/password | Employee must be in the current system | 11 | The Business wants to remove the employee from the system in case they are no longer there
12 | TS12 | 12 | Modify Employee | Employee Credentials such as username/password | Employee is in the current system | 12 | The Business wants to edit employee information in the system
13 | TS13 | 13 | Add Employee | Employee Credentials such as username/password | New employee needs to be added to the system | 13 | The business wants to add a new employee within their application
14 | TS14 | 14 | Cancel Appointment | Employee Credentials such as username/password also time/date | Patient must have booked an appointment already | 14 | The business wants to cancel an appointment for a customer
15 | TS15 | 15 | Create Appointment Time Slot | Time/Date and Patient Information | New appointment needs to be added to the system | 15 | The business wants appointments added to the system once customer books them

## TestingPlan
| Testing Plan | Team | Planned Start Date | Planned End Date | % Completed | Comments
1 | Create test scenarios |  |  |  | 100%
2 | PSOD internal validation of the scenarios |  |  |  | 100%
3 | Validate scenarios readiness for CS team |  |  |  | 100%
4 | CS team One3-PSOD integration testing iterations |  |  |  | 100%
5 | Integrations testing |  |  |  | 100%
6 | Regression testing |  |  |  | 100%
7 | CS acceptance sign-off |  |  |  | 100%
8 | One3 deployment |  |  |  | 100%
9 | PSOD deployment |  |  |  | 100%
10 | One3-PSOD Integration Live |  |  |  | 100%

## ProcessesTestCases
Target Completion | Test ID | Module | Testing Step | Path | Description | Tester | Status | Expected Result | Actual Result | Failure Scenario | Test Data (i.e. inputs) | Testers Comments | Date Tested | Test Result (Cycle 1) | Test Result (Cycle 2) | Test Result (Cycle 3) | Defect Status | Date found | Date Due | Defect Severity | Fixed by
PSOD Reported Unplanned Outage
IAAS Hosting Reported Unplanned Outage